## Slide 1
Pilot Program Roadmap
Plan and manage structured product pilots from participant selection through success evaluation and full rollout decisions.
ideaplan.io

## Slide 2
How to Use This Template
1. Define the pilot objective and measurable success criteria before selecting participants.2. Select 5-15 pilot participants. Prioritize variety across segments, company sizes, and use cases.3. Set up each participant with onboarding materials, dedicated support contacts, and feedback channels.4. Run the pilot for a fixed duration (4-12 weeks). Collect both quantitative metrics and qualitative feedback.5. Evaluate results against success criteria. Document what worked, what failed, and what to change.6. Make a clear Go/No-Go decision: expand to GA, iterate with a second pilot, or kill the initiative.7. Use the blank template to plan your pilot. The example shows an enterprise analytics feature pilot with 8 accounts.

## Slide 3
Pilot Program Plan
[Feature/Product Name] · [Start Date] – [End Date]
Select
Setup
Execute
Evaluate
Decide
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
[Task or milestone]
SUCCESS CRITERIA
Adoption Rate
[Target]
Time to Value
[Target]
NPS / CSAT
[Target]
Support Tickets
[Target]
Go/No-Go
[Target]

## Slide 4
Pilot Program Plan
Advanced Analytics Dashboard · Mar 3 – May 23, 2026
Select
Setup
Execute
Evaluate
Decide
Define criteria
Mid-market SaaS, 50-500 employees, active data team
Recruit participants
8 accounts from 3 segments (SaaS, fintech, healthcare)
Sign pilot agreements
NDA + feedback commitment, 12-week duration
Provision accounts
Sandbox environments with sample data loaded
Kick-off calls
30-min onboarding per account, record sessions
Assign CSM contacts
Dedicated CSM per 2-3 accounts, weekly check-ins
Weeks 1-4: Core usage
Track daily active users, feature adoption rate
Week 6: Mid-pilot review
Survey + 1:1 interviews, address blockers
Weeks 8-12: Deep usage
Advanced features, API integrations, custom reports
Analyze usage data
6/8 accounts hit daily use target (75%)
Score success criteria
Adoption: 75%, TTV: 3.2 days, NPS: +38
Document learnings
14 feature requests, 3 critical UX gaps identified
Go/No-Go review
Met 4/5 criteria. Gaps mitigable before GA.
GA timeline
Fix 3 UX gaps (4 weeks), then phased rollout
Rollout plan
25% of accounts in wave 1, full GA by Q3
SUCCESS CRITERIA
75%
Adoption Rate
Target: > 60%
3.2 days
Time to Value
Target: < 5 days
+38
NPS Score
Target: > +30
2.1/wk
Support Tickets
Target: < 3/wk
GO
Go/No-Go
4/5 criteria met